## Cover Page
Cover Page
Step1
Well Information:
Client: | URS | State/Prov: | PA | TARS-10 CH 30m |  | Xseries-3200XG
Client Representative: | Timothy Murin | Country: | USA | TARS-20 CH 30m |  | RCP-3200XB
Project Number: | 784 | Field: | COP 324 | TARS-10 CH 15m |  | Z-Trac
After entering Well Information click 'rename' button to rename this file for profile1 |  |  |  | TARS-20 CH 60m |  | Xseries-3201XA
Equipment Information Per Profile: |  |  |  | TARS-10 CH 100ft
Source well: | COP 324#4 | Analog Filt.well 1 / 2: |  | TARS-20 CH 100ft
Receiver Well No.1: | COP 324#6 | Gain well 1 / 2: |  | TARS-10 CH 50ft
Receiver Well No.2: | - |  |  | TARS-20 CH 200ft
Rec. Type well 1: | VSI | Source Type: | Z-Trak | Geophones
Rec. Type well 2: | None | Source S/N: | 30/31/03/06 | VSI
Rec. S/N well 1 / 2: | VSI(20) | Reciever Unit well 1:
Post Amp No well 1 / 2: |  | Source Unit: | 3129 | Step1 | COP 324Step1 | 8
TARS Comp.No well 1 / 2: |  | Reciever Unit well 2: |  | Step2 | COP 324Step2
|  |  |  | Step3 | COP 324Step3
Recording Information Per Profile: |  |  |  | Step4 | COP 324Step4
Stack: | 16 | Sweep Start Freq.: | 30 | Step5 | COP 324Step5
Sample period: | 1 ms | Sweep End Freq.: | 400 | Step6 | COP 324Step6 |  | Cover Page | Cover Page-Step1
Record length: | 11.2 s | Sweep Length: | 10.4 | Step7 | COP 324Step7 |  | Safety Meeting | Safety Meeting-Step1
Dead time: | 0 | Receiver Start Depth: | 5400 | Step8 | COP 324Step8 |  | Source warm-up form | Source warm-up form-Step1
Logging speed: | N/A | Source Start Depth: | 7275 | Step9 | COP 324Step9 |  | Source In Hole Test | Source In Hole Test-Step1
|  |  |  | Step10 | COP 324Step10 |  | Daily Acquisition rpt | Daily Acquisition rpt-Step1
|  |  |  | Step11 | COP 324Step11 |  | Survey Log | Survey Log-Step1
|  |  |  | Step12 | COP 324Step12 |  | Equip Failure Rpt | Equip Failure Rpt-Step1
|  |  |  | Step13 | COP 324Step13 |  | System Test Results | System Test Results-Step1
|  |  |  | Step14 | COP 324Step14 |  | Post Job Info | Post Job Info-Step1
|  |  |  | Step15 | COP 324Step15 |  | -
|  |  |  | Step16 | COP 324Step16
|  |  |  | Step17 | COP 324Step17
Rev.5 2013 |  |  |  | Step18 | COP 324Step18
|  |  |  | Step19 | COP 324Step19
|  |  |  | Step20 | COP 324Step20
DEEPLOOK -CS

## Safety Meeting-Step
Field Safety Meeting
Client: |  | URS |  |  |  | Date: | 2013-07-10
Project Name/No.: |  | 784
Safety Meeting-Step1
Personnel Present:
1 |  |  |  | 6
2 |  |  |  | 7
3 |  |  |  | 8
4 |  |  |  | 9
5 |  |  |  | 10
Safety Issues Discussed
Field Supervisor:
Rev.5 2013
Field Safety Meeting (continued)
A Pre-Survey safety meeting is held on-site prior to commencing operations. All crew members &
URS | representatives participated in this meeting. The planned Z-Seis operations and those of
its contractors will follow guidelines established by |  |  |  |  | URS | safety procedures and/or the
Z-Seis Safety Policies and Procedures. The issues discussed included, but are not limited to:
- Fire Procedure;
- Abandoning Rig/Location Procedure;
- Necessity for protective clothing (i.e., safety boots, hard hats, gloves);
- Safety glasses with side shields when working near or around wellheads;
- Never take short cuts when moving around the rig or units, or when using hand tools, etc.
- Never put limbs in the way of moving parts (i.e., sheave wheels, depth measure device, chains, drive shaft);
- Only Z-Seis qualified personnel to be involved in rigging Z-Seis equipment up and down;
- Review and use correct crane or mast truck operating procedures. Particular attention and review is required with crane operator to ensure communication is clear and understood;
- Third party crane operator is to take direction from only one designated Z-Seis employee during either rig up or rig down;
- The correct lifting techniques to move heavy objects;
- The correct procedure for handling and dealing with pressurized equipment (i.e., pack-offs, pressure control equipment);
- Reporting anything considered unsafe and any near misses to the shift leader and / or Field Manager;
- No smoking, lighters or matches within 50ft of wellhead, or diesel tank;
- The correct fuel transfer procedures from the diesel tank to the units;
- The correct start up procedures for the generators, light plant and other third party supplied equipment;
- Review and adhere to Source power up and shut down procedures;
- Always adhere to |  | URS | safety and work policies at wellsite;
- Awareness of danger of moving loads on cranes and actions required to minimize risks;
- Monitor each other’s work activities and ensure they are conducted safely;
- Monitor the health of employees where work activities pose potential risk to health;
- Dispose of waste safely and properly;
- Review | URS | Field Safety procedures, evacuation routes & muster location in case of fire;
- Sequence of operational work and responsible parties;
- Watch for fluid or air leaks. Monitor gauges. Use absorbent roll to clean any fluid spills;
Special points concerning the wells/location.
- Beware of ice on roads, and on wellhead equipment;
- No abnormal surface pressures anticipated at the wellheads;
- Watch for over head power line, no booms within 10 ft of power lines;
- Designate assembly area.
Rev.5 2013
DEEPLOOK -CS

## Toolstring Source
|  | for operations |  |  | for correlation
Phisical Toolstring | SN | WITH SWIVEL |  | OP delcared toolstring | WITH SWIVEL
LEH-Q | 1231 | 33 |  | MH-22 | 18.9
SAH-F | 1902 | 58.5 |  | AH-38 | 3.36 | 22.26
3211 | 1 | 12.3
3202 | 30 | 89.5 | 16.1083
3202 | 31 | 89.5
AH-184 | 964 | 24
AH-184 | 2890 | 24
AH-413 | 4 | 12.3 |  | AH-YYY | 566.2 | 566.2
AH-XXX | 9 | 12.3
AH-184 | 2987 | 24
AH-184 | 1590 | 24
3202 | 6 | 89.5
3202 | 3 | 89.5
AH-415 | 6 | 6
PBMS | 2778 | 99.4 |  | PBMS | 99.4
BNS |  | 1.7 |  | BNS | 1.7
INCH |  | 689.5 |  |  | 689.56
FT |  | 57.4583 |  |  | 57.4633
TD |  | 7320
NEW WINCH Depth/ WDD Depth |  | 7278.65
safety factor |  | 0
7278.65
Maximum START FAN Depth |  | 7275
Note on E7: X-axis depth calculated from top of LEH-QT

## Toolstring Receivers
Toolstring SN
EDTC |  | ECH
AH-199
VSPC
VSCC
VSIS-1 | 8301 | VSII-1 | 8874
VSIS-2 | 8307 | VSII-2 | 8622
VSIS-3 | 8339 | VSII-3 | 8629
VSIS-4 | 8390 | VSII-4 | 8827
VSIS-5 | 8403 | VSII-5 | 8828
VSIS-6 | 8404 | VSII-6 | 8821
VSIS-7 | 8433 | VSII-7 | 8534
VSIS-8 | 8434 | VSII-8 | 8620
VSIS-9 | 8435 | VSII-9 | 8630
VSIS-10 | 8436 | VSII-10 | W0103
VSIS-11 | 8450 | VSII-11 | 8830
VSIS-12 | 8802 | VSII-12 | 8498
VSIS-13 | 8800 | VSII-13 | 8823
VSIS-14 | 8784 | VSII-14 | 8494
VSIS-15 | 8796 | VSII-15 | 8621
VSIS-16 | 8797 | VSII-16 | W0104
VSIS-17 | 8798 | VSII-17 | 8824
VSIS-18 | 8799 | VSII-18 | 8627
VSIS-19 | 8451 | VSII-19 | 9631
VSIS-20 | 8793 | VSII-20 | W0102
VSIA-A

## Daily Acquisition rpt-Step
Daily Acquisition report
Client: | URS |  |  |  |  | Step No.: |  | 1 |  | Date: |  | 2013-07-10
Project No. | 784 |  |  |  |  | Source well: |  | COP 324#4 |  | Page: |  | 1
Field: | COP 324 |  |  |  |  | Source type: |  | Z-Trak |  | Source S/N: |  | 30/31/03/06
State/Prov: | PA |  |  |  |  | Rec. Well No.1: |  | COP 324#6 |  | Rec.S/N well 1 / 2: |  | VSI(20) |  | 0 |  | Daily Acquisition rpt-Step1
Country: | USA |  |  |  |  | Rec. Well No.2: |  | - |  | Post Amp. 1 / 2: |  | 0 |  | 0
Acquisition Days Brought Forward: |  | Total Acquisition Days: |  | 0 |  |  | Standby Days Brought Forward: |  | Total Standby Days: | 0 | Maint.time brought forward: |  | Total Maint. Time: |  | 0
Date | Time | Acquisition Day | Standby Day | Maintenance Time | Activity
2013-07-10 | 8:00 |  |  |  | Arrive at wellsite
| 8:15 |  |  |  | Safety meeting
| 8:30 |  |  |  | Start spotting equipment
| 12:30 |  |  |  | Start testing of tools & surface equipment (waiting on correct pressure eqp)
| 19:00 |  |  |  | Stop operations due to weather and lack of light plants
2013-07-11 | 6:30 |  |  |  | Arrive at wellsite, safety meeting, start operations
| 7:00 |  |  |  | Start RIH in both wells
| 8:30 |  |  |  | Truck on well 324#6 broke down (waiting on mechanic)
| 9:30 |  |  |  | Start downhole tests on source well (no clamping-due to toolstring configuration)
| 10:45 |  |  |  | Start POOH and change source toolstring configuration
| 13:00 |  |  |  | M/U source toolstring and RIH
| 17:00 |  |  |  | Start downhole tests on source well, all OK
| 17:30 |  |  |  | Finish repairs on logging truck on well 324 #6 and resume operations(correlate)
| 20:52 |  |  |  | Begin Test Fan, Shot#5, no noise shots, Tx Depth 7275, Rx Depth 7300-5400'
| 21:32 |  |  |  | End Test Fan / QC Test Fan
| 22:37 |  |  |  | Begin Fan1, Shot#81, no noise shots, Source Depth:7050
| 23:37 |  |  |  | End Fan1, split fan 1 for extra data to QC and to send to Houston
| 23:39 |  |  |  | Begin Fan1a, shot 209, no noise shots, Source Depth:6650
2013-07-12 | 2:05 |  |  |  | End Fan 1a. Stopped prematurely to change stack and sweep by recommendation from Brad
| 3:45 |  |  |  | Begin Fan1b noise shots. 16x16, 50' interval 10.4sweep, 0.8listen, 11.2record, Vib stored #13
| 3:56 |  |  |  | End Fan1b, Voltage clipping with new parameters, pelton attenuator adjustment required.
| 4:23 |  |  |  | Begin Fan1c noise shots file#615
| 5:07 |  |  |  | End Fan1c, Maxwell crash
| 5:48 |  |  |  | Begin Fan1d
| 6:08 |  |  |  | End Fan1e, Maxwell crash, only noise shots were taken
| 6:40 |  |  |  | Begin Fan1e, elevated Rx wireless bridge for better line of site.
| 11:00 |  |  |  | End of Fan1e, wrong sweep loaded in VibPro
| 11:30 |  |  |  | UPS died
| 12:10 |  |  |  | Begin of Fan1g; 16x16, 50' interval 10.4sweep, 0.8listen, 11.2record, Vib stored #13
| 18:37 |  |  |  | End of Fan1g
| 18:45 |  |  |  | Begin of Fan1h
| 18:50 |  |  |  | Noise test
| 18:53 |  |  |  | maxwell crash
| 19:13 |  |  |  | Begin of Fan1i noise
| 21:59 |  |  |  | End Fan1i
Move receiver toolstring 50' to 5350, Source to 7275', trouble anchoring 3 tools 14,17,18
| 23:27 |  |  |  | Begin Fan2;16x16, 50' interval 10.4sweep, 0.8listen, 11.2record, Vib stored #13
| 23:31 |  |  |  | Maxwell crash during noise shots
| 23:48 |  |  |  | Begin Fan2a
2013-07-13 | 3:12 |  |  |  | End Fan2a
| 3:36 |  |  |  | Begin Fan2b noise shots
| 3:37 |  |  |  | End Fan2b Maxwell crash during noise shots
| 3:57 |  |  |  | Begin Fan2c noise shots
| 4:08 |  |  |  | about to start power shots when OVP light on sorenson was illuminated. Swapped panel
Rev.5 2013
DEEPLOOK -CS
Note on B11: Stuart Douglas: Enter amount from 'Total acquisition Days' column from previous sheet.
Note on I11: Stuart Douglas: Enter amount from 'Total standby days' column on previous sheet.
Note on M11: Stuart Douglas: Enter total from previous sheet
Note on E12: Stuart Douglas: Maintenance time includes any time spent repairing equipment, tool failures, fiber breakage etc.
Note on C13: Stuart Douglas: Enter a '1', '0.5' or '0' for each day. Acquisition day means recording data or tie-in.
Note on D13: Stuart Douglas: Enter a '1', '0.5' or '0' for each day. Standby day is a day on standby that is not Z-Seis's fault.
Note on E13: Stuart Douglas: Enter time in hours- round to nearest half hour

## Daily Acquisition rpt-Step (2)
Daily Acquisition report
Client: | URS |  |  |  |  | Step No.: |  | 1 |  | Date: |  | 2013-07-10
Project No. | 784 |  |  |  |  | Source well: |  | COP 324#4 |  | Page: |  | 2
Field: | COP 324 |  |  |  |  | Source type: |  | Z-Trak |  | Source S/N: |  | 30/31/03/06
State/Prov: | PA |  |  |  |  | Rec. Well No.1: |  | COP 324#6 |  | Rec.S/N well 1 / 2: |  | VSI(20) |  | 0 |  |  | Daily Acquisition rpt-Step1
Country: | USA |  |  |  |  | Rec. Well No.2: |  | - |  | Post Amp. 1 / 2: |  | 0 |  | 0
Acquisition Days Brought Forward: |  | Total Acquisition Days: |  | 0 |  |  | Standby Days Brought Forward: |  | Total Standby Days: | 0 | Maint.time brought forward: |  | Total Maint. Time: |  | 0
Date | Time | Acquisition Day | Standby Day | Maintenance Time | Activity
2013-07-13
| 4:45 |  |  |  | Begin Fan2c Power shots
| 5:06 |  |  |  | End Fan2c, Maxwell Crash, moved 75' will restart at 6375 for Fan2d, Reboot Maxwell computer
| 5:22 |  |  |  | Begin Fan2d noise
| 5:29 |  |  |  | End Fan2d, Maxwell Crash during noise shots, Reboot Maxwell computer and load older patch
unsuccessfull
| 6:30 |  |  |  | Install initial SP and create a new job (Z trac and HFM2)
| 7:20 |  |  |  | Start Fan2f
| 10:40 |  |  |  | Getting radio delays, source not sweeping for all shots. End of Fan2f
| 12:00 |  |  |  | Swap vibros, no result, replace on radio on source side, all OK
| 13:00 |  |  |  | Perform sweep test, monitor current values on magna power
| 14:00 |  |  |  | Start Fan2h noise
| 17:30 |  |  |  | End of Fan2h and pre-frc profile
| 18:00 |  |  |  | POOH and rig down source --> rig up HFM VSI-12
HFM ACQUISITION
2013-07-19 | 13:30 |  |  |  | Start rig up Z-Trac
| 15:30 |  |  |  | Surface testing
| 16:30 |  |  |  | tool at surface
| 19:00 |  |  |  | Night crew on location
| 23:00 |  |  |  | Start in the whole with z-track
POST HFM
2013-07-20 | 1:15 |  |  |  | at tape mark and ready to go 7275'
| 3:27 |  |  |  | Begin noise shots for background noise fan. (16x16)x5
| 4:34 |  |  |  | Begin noise shots for Fan3
| 4:44 |  |  |  | End fan due to z-trac not being driven with every sweep. Troubleshoot.
| 5:35 |  |  |  | Swapped radios and all appears to be well now. | [10 empty] | The Vibpro was also switched but did not resolve the problem
| 5:38 |  |  |  | Begin noise shots for Fan3a
| 7:40 |  |  |  | eof 3a
| 8:00 |  |  |  | St Fan3b
| 12:29 |  |  |  | eof 3b
no 3c void
| 13:00 |  |  |  | St. Fan3d
| 16:02 |  |  |  | eof 3-D
| 18:44 |  |  |  | St.fan 4
| 18:54 |  |  |  | End Fan4, Sweep signal for Y axis on receiver side distorted. Reseat cards in Rx Vibrpro | [10 empty] | The WSAM was also changed out but did not affect the signal.
| 19:39 |  |  |  | Start fan4a
2013-07-21 | 0:15 |  |  |  | End Fan4a
| 0:23 |  |  |  | Start fan4b
| 4:47 |  |  |  | End Fan4b
Rev.5 2013
DEEPLOOK -CS
Note on B11: Stuart Douglas: Enter amount from 'Total acquisition Days' column from previous sheet.
Note on I11: Stuart Douglas: Enter amount from 'Total standby days' column on previous sheet.
Note on M11: Stuart Douglas: Enter total from previous sheet
Note on E12: Stuart Douglas: Maintenance time includes any time spent repairing equipment, tool failures, fiber breakage etc.
Note on C13: Stuart Douglas: Enter a '1', '0.5' or '0' for each day. Acquisition day means recording data or tie-in.
Note on D13: Stuart Douglas: Enter a '1', '0.5' or '0' for each day. Standby day is a day on standby that is not Z-Seis's fault.
Note on E13: Stuart Douglas: Enter time in hours- round to nearest half hour

## Daily Acquisition rpt-Step (3)
Daily Acquisition report
Client: | URS |  |  |  |  | Step No.: |  | 1 |  | Date: |  | 2013-07-21
Project No. | 784 |  |  |  |  | Source well: |  | COP 324#4 |  | Page: |  | 3
Field: | COP 324 |  |  |  |  | Source type: |  | Z-Trak |  | Source S/N: |  | 30/31/03/06
State/Prov: | PA |  |  |  |  | Rec. Well No.1: |  | COP 324#6 |  | Rec.S/N well 1 / 2: |  | VSI(20) |  | 0 |  | Daily Acquisition rpt-Step1
Country: | USA |  |  |  |  | Rec. Well No.2: |  | - |  | Post Amp. 1 / 2: |  | 0 |  | 0
Acquisition Days Brought Forward: |  | Total Acquisition Days: |  | 0 |  |  | Standby Days Brought Forward: |  | Total Standby Days: | 0 | Maint.time brought forward: |  | Total Maint. Time: |  | 0
Date | Time | Acquisition Day | Standby Day | Maintenance Time | Activity
2013-07-21 | 6:01 |  |  |  | Begin Fan4cbu, com error on shuttle 10 x-axis shot 1560 - 1690 during Fan4b
| 6:11 |  |  |  | Start fan4cbu
| 7:16 |  |  |  | End Fan4cbu
| 8:20 |  |  |  | Start Fan5
| 13:17 |  |  |  | End Fan5
| 13:25 |  |  |  | Start Fan5a
| 17:54 |  |  |  | End Fan 5a
Night Crew On Duty
| 18:57 |  |  |  | Start Fan 6 noise shots
| 19:08 |  |  |  | End Fan6 - Maxwell self aborted firing loop causing a missed shot
| 20:15 |  |  |  | Start Fan6a
| 21:26 |  |  |  | End Fan6a - Maxwell self aborted firing loop causing a missed shot, last good shot 380 @ 7050
| 21:23 |  |  |  | Start Fan6b
| 21:55 |  |  |  | End of Fan6b - Vibro warning, Z-trac stopped sweeping
| 22:01 |  |  |  | Start Fan6c
2013-07-22 | 1:38 |  |  |  | Error on Maxwell - Failed to connect to Data Server (VSI Stack-Off Shot Processing Module)
| 2:11 |  |  |  | End Fan6c
| 2:24 |  |  |  | Start Fan6e, Fan6d was voided due to incorrect parameters set, no shots triggered
Error on Maxwell - Failed to connect to Data Server (VSI Stack-Off Shot Processing Module)
| 3:50 |  |  |  | End Fan6e
Restart Maxwell and MCMP
| 4:12 |  |  |  | Start Fan6f
| 8:32 |  |  |  | End of Fan6f
Start poh
| 11:15 |  |  |  | Finish rig down. END OF JOB
Rev.5 2013
DEEPLOOK -CS
Note on B11: Stuart Douglas: Enter amount from 'Total acquisition Days' column from previous sheet.
Note on I11: Stuart Douglas: Enter amount from 'Total standby days' column on previous sheet.
Note on M11: Stuart Douglas: Enter total from previous sheet
Note on E12: Stuart Douglas: Maintenance time includes any time spent repairing equipment, tool failures, fiber breakage etc.
Note on C13: Stuart Douglas: Enter a '1', '0.5' or '0' for each day. Acquisition day means recording data or tie-in.
Note on D13: Stuart Douglas: Enter a '1', '0.5' or '0' for each day. Standby day is a day on standby that is not Z-Seis's fault.
Note on E13: Stuart Douglas: Enter time in hours- round to nearest half hour

## Pre-Frac Survey Log 1
Survey Log
Client Company: |  | URS |  |  |  |  | Well ID: | Type: |  | Level Spacing | Stack (EG&G): | 16 | Sweep Length: | 10.4 | Step No.: |  | 1 |  | Page No.: |  | 1 |  | Survey Log-Step1
Client Rep: |  | Timothy Murin | [12 empty] | Date: |  | 2013-07-11
Field: |  | COP 324 |  |  |  |  | COP 324#4 | Source |  | 50 | Sample period: | 1 ms | Dead Time: | 0 | Depth Units: |  | Feet
State/Prov.: |  | PA |  |  |  |  | COP 324#6 | Receiver 1 |  | 50 | Record Length: | 11.2 s |  |  | Receiver Type well 1 / 2: |  | VSI |  | None | [6 empty] | #NAME?
Country: |  | USA |  |  |  |  | - | Receiver 2 |  |  | Start Freq.: | 30 |  |  | Notes: | [7 empty] | Meters
Job No.: |  | 784 | [5 empty] | Durant |  |  | End Freq.: | 400 | [10 empty] | Feet
Fan No. | File Number | Shot Number | Source Depth | Receiver |  | Receiver | Time | Tape Number: | Coments | [10 empty] | Log file No. | Av. Noise | QC Y/N? | Acquisition | QC | Winch Op
Test Fan | 5 | 5 | 7275 | 5400 |  | 7300 | 20:52 |  | Noise N/A | [10 empty] | 1 |  |  | Stuart Douglas | Carl Addington | Freddie Primus
|  | 5 | [6 empty] | Go Power | [13 empty] | Gordon Stenseng | Brad Bryons | Dave Vanderwater
|  | 76 | 7075 |  |  |  | 21:32 |  | End of Fan | [13 empty] | Leigh Sauer | Bruce Marion | Marcello Di Campli
[23 empty] | Alex Plotnikov | Dave Richards | Leigh Sauer
Fan1 | 81 | 81 | 7050 | 5400 |  | 7300 | 22:37 |  | Noise N/A | [10 empty] | 2
|  | 81 | [6 empty] | Go Power | [13 empty] | Dave Vanderwater | Jim Minto | Gary Boche
|  | 208 | 6675 |  |  |  | 23:37 |  | End of Fan, no issues. Split fan to get extra data to QC and send to Houston | [13 empty] | Carl Addington | Stuart Douglas | Gordon Stenseng
[23 empty] | Jim Minto | Alex Plotnikov | Stuart Douglas
Fan1a | 209 | 209 | 6650 | 5400 |  | 7300 | 23:39 |  | Noise N/A | [10 empty] | 3 |  |  | Pat Cummins | Gordon Stenseng | Alex Plotnikov
|  | 209 | [6 empty] | Go Power | [13 empty] | Rick Strange |  | Pat Cummins
|  | 576 | 5525 |  |  |  | 2:05 |  | End of Fan | [13 empty] | Larry Paterson |  | Camillo Zamponi
[23 empty] | Luke Wilkens |  | Tony Lagman
Fan1b | 579 | 579 | 7275 | 5400 |  | 7300 | 3:43 |  | Noise (Recorded with incorrect sweep - unnoticed) | [10 empty] | 4 |  |  | James Minto |  | Stuart Douglas
|  | 611 | [6 empty] | Go Power, 16x16, 50' interval 10.4sweep, 0.8listen, 11.2record, Vib stored #13 | [15 empty] | Rick Strange
|  | 612 | 7275 |  |  |  | 3:56 |  | End of Fan (Voltage clipping, need to adjust potentiometer) | [15 empty] | Larry Paterson
Luke Wilkens
Fan1c | 615 | 615 | 7275 | 5400 |  | 7300 | 4:23 |  | Noise (Recorded with incorrect sweep - unnoticed) | [10 empty] | 5 |  |  |  |  | Andre Salesse
|  | 647 |  |  |  |  | 4:33 |  | Go Power | [15 empty] | Conor Minto
|  | 726 | 7175 |  |  |  | 5:07 |  | End of Fan (Maxwell Crash) | [15 empty] | James Minto
Receiver well: |  |  | VSI(20) |  | 0 |  | Source S/N: |  |  | 30/31/03/06 | [5 empty] | Source Unit No.: |  | 3129
TARS Post Amp S/N well 1 / 2: |  |  | 0 |  | 0 |  | Source Type: |  |  | Z-Trak |  |  | Logging Speed: |  |  | Rec.Unit well 1/2: |  | 0 |  | 0
TARS Comp.No.well 1 / 2: |  |  | 0 |  | 0 |  | Volts Pk-Pk: |  |  | 7.4 | Amps Pk-Pk: |  |  |  | 4 | Acquisition Op.: |  | G Baldovin / J Miller
Receiver Gain well: |  |  | x16 |  | 0 |  | Drive Level: |  |  | 302 | [5 empty] | QC Op.: |  | Brad Carl |  |  |  |  | In
Analog Filter well 1 / 2: |  |  | 0 |  | 0 |  | SGF File Name: |  |  | 3129 | [5 empty] | Winch Op.: |  | J Chavez / D Vandawater |  |  |  |  | Out
Rev.5 2013
DEEPLOOK -CS

## Pre-Frac Survey Log 2
Survey Log
Client Company: |  | URS |  |  |  |  | Well ID: | Type: |  | Level Spacing | Stack (EG&G): | 16 | Sweep Length: | 10.4 | Step No.: |  | 1 |  | Page No.: |  | 2 |  |  | Survey Log-Step1
Client Rep: |  | Timothy Murin | [12 empty] | Date: |  | 2013-07-12
Field: |  | COP 324 |  |  |  |  | COP 324#4 | Source |  | 50 | Sample period: | 1 ms | Dead Time: | 0 | Depth Units: |  | Feet
State/Prov.: |  | PA |  |  |  |  | COP 324#6 | Receiver 1 |  | 50 | Record Length: | 11.2 s |  |  | Receiver Type well 1 / 2: |  | VSI |  | None | [7 empty] | #NAME?
Country: |  | USA |  |  |  |  | - | Receiver 2 |  |  | Start Freq.: | 30 |  |  | Notes: | [8 empty] | Meters
Job No.: |  | 784 | [5 empty] | Durant |  |  | End Freq.: | 400 | [11 empty] | Feet
Fan No. | File Number | Shot Number | Source Depth | Receiver |  | Receiver | Time | Tape Number: | Coments | [10 empty] | Log file No. | Av. Noise | QC Y/N? |  | Acquisition | QC | Winch Op
Fan1e | 751 | 751 | 7275 | 5400 |  | 7300 | 6:40 |  | Noise | [10 empty] | 7 |  |  |  | Stuart Douglas | Carl Addington | Freddie Primus
|  | 783 |  |  |  |  | 6:51 |  | Go Power | [14 empty] | Gordon Stenseng | Brad Bryons | Dave Vanderwater
[7 empty] | 11:00 |  | End of Fan (Recorded with incorrect sweep - noticed) | [14 empty] | Leigh Sauer | Bruce Marion | Marcello Di Campli
[24 empty] | Alex Plotnikov | Dave Richards | Leigh Sauer
Fan1f | 1440 | 1440 | 7275 | 5400 |  | 7300 | 11:29 |  | Noise | [10 empty] | 8
[7 empty] | 11:40 |  | End of Fan (UPS problems) | [14 empty] | Dave Vanderwater | Jim Minto | Gary Boche
[24 empty] | Carl Addington | Stuart Douglas | Gordon Stenseng
Fan1g | 1474 | 1474 | 7275 | 5400 |  | 7300 | 12:10 |  | Noise | [10 empty] | 9 |  |  |  | Jim Minto | Alex Plotnikov | Stuart Douglas
|  | 1506 |  |  |  |  | 12:20 |  | Go Power | [14 empty] | Pat Cummins | Gordon Stenseng | Alex Plotnikov
|  | 2561 | 5650 |  |  |  | 18:43 |  | End of Fan | [14 empty] | Rick Strange |  | Pat Cummins
[24 empty] | Larry Paterson |  | Camillo Zamponi
Fan1h | 2563 | 2563 | 5625 | 5400 |  | 7300 | 18:50 |  | Noise | [10 empty] | 10 |  |  |  | Luke Wilkens |  | Tony Lagman
[9 empty] | End of Fan (Maxwell Crash) | [14 empty] | James Minto |  | Stuart Douglas
Rick Strange
Fan1i | 2577 | 2577 | 5625 | 5400 |  | 7300 | 19:08 |  | Noise | [10 empty] | 11 | [5 empty] | Larry Paterson
|  | 2609 |  |  |  |  | 19:24 |  | Go Power | [16 empty] | Luke Wilkens
|  | 3088 | 4900 |  |  |  | 21:59 |  | End of Fan | [16 empty] | Andre Salesse
Conor Minto
Fan2 | 3093 | 3093 | 7275 | 5350 |  | 7250 | 23:27 |  | Noise | [10 empty] | 12 |  |  | Station 13 |  |  | James Minto
[7 empty] | 23:31 |  | End of Fan (Maxwell Crash)
Receiver well: |  |  | VSI(20) |  | 0 |  | Source S/N: |  |  | 30/31/03/06 | [5 empty] | Source Unit No.: |  | 3129
TARS Post Amp S/N well 1 / 2: |  |  | 0 |  | 0 |  | Source Type: |  |  | Z-Trak |  |  | Logging Speed: |  |  | Rec.Unit well 1/2: |  | 0 |  | 0
TARS Comp.No.well 1 / 2: |  |  | 0 |  | 0 |  | Volts Pk-Pk: |  |  | 7.4 | Amps Pk-Pk: |  |  |  | 4 | Acquisition Op.: |  | G Baldovin / J Miller
Receiver Gain well: |  |  | x16 |  | 0 |  | Drive Level: |  |  | 386 | [5 empty] | QC Op.: |  | Brad Carl | [5 empty] | In
Analog Filter well 1 / 2: |  |  | 0 |  | 0 |  | SGF File Name: |  |  | 3129 | [5 empty] | Winch Op.: |  | J Chavez / D Vandawater | [5 empty] | Out
Rev.5 2013
DEEPLOOK -CS

## Pre-Frac Survey Log 3
Survey Log
Client Company: |  | URS |  |  |  |  | Well ID: | Type: |  | Level Spacing | Stack (EG&G): | 16 | Sweep Length: | 10.4 | Step No.: |  | 1 |  | Page No.: |  | 3 |  |  | Survey Log-Step1
Client Rep: |  | Timothy Murin | [12 empty] | Date: |  | 2013-07-13
Field: |  | COP 324 |  |  |  |  | COP 324#4 | Source |  | 50 | Sample period: | 1 ms | Dead Time: | 0 | Depth Units: |  | Feet
State/Prov.: |  | PA |  |  |  |  | COP 324#6 | Receiver 1 |  | 50 | Record Length: | 11.2 s |  |  | Receiver Type well 1 / 2: |  | VSI |  | None | [7 empty] | #NAME?
Country: |  | USA |  |  |  |  | - | Receiver 2 |  |  | Start Freq.: | 30 |  |  | Notes: | [8 empty] | Meters
Job No.: |  | 784 | [5 empty] | Durant |  |  | End Freq.: | 400 | [11 empty] | Feet
Fan No. | File Number | Shot Number | Source Depth | Receiver |  | Receiver | Time | Tape Number: | Coments | [10 empty] | Log file No. | Av. Noise | QC Y/N? |  | Acquisition | QC | Winch Op
Fan2a | 3107 | 3107 | 7275 | 5350 |  | 7250 | 23:48 |  | Noise | [10 empty] | 13 |  |  | Station 14 | Stuart Douglas | Carl Addington | Freddie Primus
|  | 3139 |  |  |  |  | 0:04 |  | Go Power | [14 empty] | Gordon Stenseng | Brad Bryons | Dave Vanderwater
|  | 3715 | 6400 |  |  |  | 3:12 |  | End of Fan | [14 empty] | Leigh Sauer | Bruce Marion | Marcello Di Campli
[24 empty] | Alex Plotnikov | Dave Richards | Leigh Sauer
Fan2b | 3717 | 3717 | 6375 | 5350 |  | 7250 | 3:36 |  | Noise | [10 empty] | 14 |  |  | Station 15
|  | 3724 | 6375 |  |  |  | 3:37 |  | End of Fan (Maxwell Crash) | [14 empty] | Dave Vanderwater | Jim Minto | Gary Boche
[24 empty] | Carl Addington | Stuart Douglas | Gordon Stenseng
Fan2c | 3729 | 3729 | 6375 | 5350 |  | 7250 | 3:57 |  | Noise | [10 empty] | 15 |  |  | Station 16 | Jim Minto | Alex Plotnikov | Stuart Douglas
|  | 3761 |  |  |  |  | 4:45 |  | Go Power | [14 empty] | Pat Cummins | Gordon Stenseng | Alex Plotnikov
|  | 3822 | 6300 |  |  |  | 5:06 |  | End of Fan (Maxwell Crash) | [14 empty] | Rick Strange |  | Pat Cummins
[24 empty] | Larry Paterson |  | Camillo Zamponi
Fan2d | 3827 | 3827 | 6375 | 5350 |  | 7250 | 5:22 |  | Noise | [10 empty] | 16 |  |  | Station 17 | Luke Wilkens |  | Tony Lagman
|  |  | 6375 |  |  |  | 5:29 |  | End of Fan (Maxwell Crash) | [14 empty] | James Minto |  | Stuart Douglas
Rick Strange
Fan2e |  |  | 6375 | 5350 |  | 7250 | 6:50 |  | Noise | [10 empty] | 17 |  |  | Station 18 |  |  | Larry Paterson
[7 empty] | 7:10 |  | End of Fan (Maxwell Crash) | [16 empty] | Luke Wilkens
Andre Salesse
Fan2f | 3 | 3 | 6375 | 5350 |  | 7250 | 7:23 |  | Noise | [10 empty] | 18 |  |  | Staion 19 |  |  | Conor Minto
|  | 35 |  |  |  |  | 7:51 |  | Go Power | [16 empty] | James Minto
|  | 530 | 5625 |  |  |  | 10:50 |  | End of Fan (Radio Delay problems-last good shot 418 @ 5800ft)
Fan2h | 758 | 758 | 5825 | 5350 |  | 7250 | 13:58 |  | Noise | [10 empty] | 20 |  |  | Station 20
|  | 790 |  |  |  |  | 14:08 |  | Go Power
|  | 1397 | 4900 |  |  |  | 17:31 |  | End of Fan
Receiver well: |  |  | VSI(20) |  | 0 |  | Source S/N: |  |  | 3129 | [5 empty] | Source Unit No.: |  | 0
TARS Post Amp S/N well 1 / 2: |  |  | 0 |  | 0 |  | Source Type: |  |  | 0 |  |  | Logging Speed: |  |  | Rec.Unit well 1/2: |  | 0 |  | 0
TARS Comp.No.well 1 / 2: |  |  | 0 |  | 0 |  | Volts Pk-Pk: |  |  | 7.4 | Amps Pk-Pk: |  |  |  | 4 | Acquisition Op.: |  | G Baldovin / J Miller | [5 empty] | In
Receiver Gain well: |  |  | Z-Trak |  | 0 |  | Amp.Att.: |  |  | 386 | [5 empty] | QC Op.: |  | Brad Carl | [5 empty] | Out
Analog Filter well 1 / 2: |  |  | 0 |  | 0 |  |  |  |  | 3129 | [5 empty] | Winch Op.: |  | J Chavez / D Vandawater
Rev.5 2013
DEEPLOOK -CS

## Post-Frac Survey Log 1
Survey Log
Client Company: |  | URS |  |  |  |  | Well ID: | Type: |  | Level Spacing | Stack (EG&G): | 16 | Sweep Length: | 10.4 | Step No.: |  | 1 |  | Page No.: |  | 5 |  | Survey Log-Step1
Client Rep: |  | Timothy Murin | [12 empty] | Date: |  | 2013-07-20
Field: |  | COP 324 |  |  |  |  | COP 324#4 | Source |  | 50 | Sample period: | 1 ms | Dead Time: | 0 | Depth Units: |  | Feet
State/Prov.: |  | PA |  |  |  |  | COP 324#6 | Receiver 1 |  | 50 | Record Length: | 11.2 s |  |  | Receiver Type well 1 / 2: |  | VSI |  | None | [6 empty] | #NAME?
Country: |  | USA |  |  |  |  | - | Receiver 2 |  |  | Start Freq.: | 30 |  |  | Notes: | [7 empty] | Meters
Job No.: |  | 784 | [5 empty] | Durant |  |  | End Freq.: | 400 | [10 empty] | Feet
Fan No. | File Number | Shot Number | Source Depth | Receiver |  | Receiver | Time | Tape Number: | Coments | [10 empty] | Log file No. | Av. Noise | QC Y/N? | Acquisition | QC | Winch Op
Background5x | 7 | 7 | 7275 | 6200 |  | 7300 | 3:27 |  | Noise Post Frac | [13 empty] | Stuart Douglas | Carl Addington | Freddie Primus
[9 empty] | Go Power | [13 empty] | Gordon Stenseng | Brad Bryons | Dave Vanderwater
|  | 166 | 7275 |  |  |  | 4:16 |  | End of Fan
[23 empty] | Leigh Sauer | Bruce Marion | Marcello Di Campli
Fan3 | 442 | 442 | 7275 | 6200 |  | 7300 | 4:34 |  | Noise | [10 empty] | 4 |  |  | Alex Plotnikov | Dave Richards | Leigh Sauer
|  | 474 |  |  |  |  | 4:44 |  | Go Power
|  | 543 | 7275 |  |  |  | 5:33 |  | End of Fan (Z-trac not being driven during evey sweep) | [13 empty] | Dave Vanderwater | Jim Minto | Gary Boche
[23 empty] | Jim Minto | Alex Plotnikov | Stuart Douglas
Fan3a | 547 | 547 | 7275 | 6200 |  | 7300 | 5:38 |  | Noise | [10 empty] | 5 |  |  | Pat Cummins | Gordon Stenseng | Alex Plotnikov
|  | 579 |  |  |  |  | 5:47 |  | Go Power | [13 empty] | Rick Strange |  | Pat Cummins
|  | 898 | 6800 |  |  |  | 7:40 |  | End of Fan | [13 empty] | Larry Paterson |  | Camillo Zamponi
[23 empty] | Luke Wilkens |  | Tony Lagman
Fan3b | 899 | 899 | 6775 | 6200 |  | 7300 | 8:00 |  | Noise | [10 empty] | 6 |  |  | James Minto |  | Stuart Douglas
|  | 931 |  |  |  |  | 9:09 |  | Go Power | [15 empty] | Rick Strange
|  | 1666 | 5650 |  |  |  | 12:35 |  | End of Fan | [15 empty] | Larry Paterson
Luke Wilkens
Fan3c | 1667 | 1667 | 5625 | 6200 |  | 7300 | 12:40 |  | Noise | [10 empty] | 7 |  |  |  |  | Andre Salesse
[9 empty] | Go Power | [15 empty] | Conor Minto
|  |  | 5625 |  |  |  | 12:50 |  | End of Fan (MaxWell crashed Void fan 3c) | [15 empty] | James Minto
Fan3 | 1678 | 1678 | 5625 | 6200 |  | 7300 | 12:58 |  | Noise - Fan3 was actived instead of Fan3d by accident | [10 empty] | 8
|  | 1710 |  |  |  |  | 13:08 |  | Go Power
|  | 2189 | 4900 |  |  |  | 14:10 |  | End of Fan
Receiver well: |  |  | VSI(12) |  | 0 |  | Source S/N: |  |  | 30/31/03/06 | [5 empty] | Source Unit No.: |  | 3129
TARS Post Amp S/N well 1 / 2: |  |  | 0 |  | 0 |  | Source Type: |  |  | Z-Trak |  |  | Logging Speed: |  |  | Rec.Unit well 1/2: |  | 0 |  | 0
TARS Comp.No.well 1 / 2: |  |  | 0 |  | 0 |  | Volts Pk-Pk: |  |  | 7.4 | Amps Pk-Pk: |  |  |  | 4 | Acquisition Op.: |  | G Baldovin / J Miller
Receiver Gain well: |  |  | 0 |  | 0 |  | Drive Level: |  |  | 386 | [5 empty] | QC Op.: |  | Brad / Carl |  |  |  |  | In
Analog Filter well 1 / 2: |  |  | 0 |  | 0 |  | SGF File Name: |  |  | 3129 | [5 empty] | Winch Op.: |  | J Chavez / D Vandawater |  |  |  |  | Out
Rev.5 2013
DEEPLOOK -CS

## Post-Frac Survey Log 2
Survey Log
Client Company: |  | URS |  |  |  |  | Well ID: | Type: |  | Level Spacing | Stack (EG&G): | 16 | Sweep Length: | 10.4 | Step No.: |  | 1 |  | Page No.: |  | 6 |  | Survey Log-Step1
Client Rep: |  | Timothy Murin | [12 empty] | Date: |  | 2013-07-20
Field: |  | COP 324 |  |  |  |  | COP 324#4 | Source |  | 50 | Sample period: | 1 ms | Dead Time: | 0 | Depth Units: |  | Feet
State/Prov.: |  | PA |  |  |  |  | COP 324#6 | Receiver 1 |  | 50 | Record Length: | 11.2 s |  |  | Receiver Type well 1 / 2: |  | VSI |  | None | [6 empty] | #NAME?
Country: |  | USA |  |  |  |  | - | Receiver 2 |  |  | Start Freq.: | 30 |  |  | Notes: |  | Post Frac | [5 empty] | Meters
Job No.: |  | 784 | [5 empty] | Durant |  |  | End Freq.: | 400 | [10 empty] | Feet
Fan No. | File Number | Shot Number | Source Depth | Receiver |  | Receiver | Time | Tape Number: | Coments | [10 empty] | Log file No. | Av. Noise | QC Y/N? | Acquisition | QC | Winch Op
Fan4 | 22 | 22 | 7275 | 6150 |  | 7250 | 18:44 |  | Noise | [10 empty] | 2 |  |  | Stuart Douglas | Carl Addington | Freddie Primus
[9 empty] | Go Power | [13 empty] | Gordon Stenseng | Brad Bryons | Dave Vanderwater
|  |  | 7275 |  |  |  | 18:54 |  | End of Fan (Sweep signal distorted for Y noise shots. Reset cards in Rx vibpro)
[23 empty] | Leigh Sauer | Bruce Marion | Marcello Di Campli
Fan4a | 91 | 91 | 7275 | 6150 |  | 7250 | 19:39 |  | Noise | [10 empty] | 3 |  |  | Alex Plotnikov | Dave Richards | Leigh Sauer
|  | 139 |  |  |  |  | 19:54 |  | Go Power
|  | 890 | 6100 |  |  |  | 0:15 |  | End of Fan | [13 empty] | Dave Vanderwater | Jim Minto | Gary Boche
[23 empty] | Carl Addington | Stuart Douglas | Gordon Stenseng
Fan4b | 891 | 891 | 6075 | 6150 |  | 7250 | 0:23 |  | Noise | [10 empty] | 4 |  |  | Pat Cummins | Gordon Stenseng | Alex Plotnikov
|  | 923 |  |  |  |  | 0:32 |  | Go Power | [13 empty] | Rick Strange |  | Pat Cummins
|  | 1690 | 4900 |  |  |  | 4:47 |  | End of Fan (Com error on shuttle 10, x-axis shot 1560 -1690 during Fan4b) | [13 empty] | Larry Paterson |  | Camillo Zamponi
[23 empty] | Luke Wilkens |  | Tony Lagman
Fan4cbu | 1691 | 1691 | 5175 | 6150 |  | 7250 | 6:01 |  | Noise | [10 empty] | 5 |  |  | James Minto |  | Stuart Douglas
|  | 1773 |  |  |  |  | 6:11 |  | Go Power | [15 empty] | Rick Strange
|  | 1914 | 4900 |  |  |  | 7:16 |  | End of Fan | [15 empty] | Larry Paterson
Luke Wilkens
Fan5 | 6 | 6 | 7275 | 5200 |  | 6300 | 8:32 |  | Noise | [10 empty] | 2 |  |  |  |  | Andre Salesse
|  | 38 |  |  |  |  | 8:44 |  | Go Power | [15 empty] | Conor Minto
|  | 805 | 6100 |  |  |  | 13:17 |  | End of Fan | [15 empty] | James Minto
Fan5a | 806 | 806 | 6075 | 5200 |  | 6300 | 13:25 |  | Noise | [10 empty] | 3
|  | 838 |  |  |  |  | 13:36 |  | Go Power
|  | 1605 | 4900 |  |  |  | 17:54 |  | End of Fan
Receiver well: |  |  | VSI(12) |  | 0 |  | Source S/N: |  |  | 30/31/03/06 | [5 empty] | Source Unit No.: |  | 3129
TARS Post Amp S/N well 1 / 2: |  |  | 0 |  | 0 |  | Source Type: |  |  | Z-Trak |  |  | Logging Speed: |  |  | Rec.Unit well 1/2: |  | 3019 |  | 0
TARS Comp.No.well 1 / 2: |  |  | 0 |  | 0 |  | Volts Pk-Pk: |  |  | 7.4 | Amps Pk-Pk: |  |  |  | 4 | Acquisition Op.: |  | G Baldovin / J Miller
Receiver Gain well: |  |  | 0 |  | 0 |  | Drive Level: |  |  | 386 | [5 empty] | QC Op.: |  | Brad / Carl |  |  |  |  | In
Analog Filter well 1 / 2: |  |  | 0 |  | 0 |  | SGF File Name: |  |  | 3129 | [5 empty] | Winch Op.: |  | J Chavez / D Vandawater |  |  |  |  | Out
Rev.5 2013
DEEPLOOK -CS

## Post-Frac Survey Log 3
Survey Log
Client Company: |  | URS |  |  |  |  | Well ID: | Type: |  | Level Spacing | Stack (EG&G): | 16 | Sweep Length: | 10.4 | Step No.: |  | 1 |  | Page No.: |  | 7 |  | Survey Log-Step1
Client Rep: |  | Timothy Murin | [12 empty] | Date: |  | 2013-07-21
Field: |  | COP 324 |  |  |  |  | COP 324#4 | Source |  | 50 | Sample period: | 1 ms | Dead Time: | 0 | Depth Units: |  | Feet
State/Prov.: |  | PA |  |  |  |  | COP 324#6 | Receiver 1 |  | 50 | Record Length: | 11.2 s |  |  | Receiver Type well 1 / 2: |  | VSI |  | None | [6 empty] | #NAME?
Country: |  | USA |  |  |  |  | - | Receiver 2 |  |  | Start Freq.: | 30 |  |  | Notes: |  | Post Frac | [5 empty] | Meters
Job No.: |  | 784 | [5 empty] | Durant |  |  | End Freq.: | 400 | [10 empty] | Feet
Fan No. | File Number | Shot Number | Source Depth | Receiver |  | Receiver | Time | Tape Number: | Coments | [10 empty] | Log file No. | Av. Noise | QC Y/N? | Acquisition | QC | Winch Op
Fan6 | 9 | 9 | 7275 | 5150 |  | 6250 | 18:57 |  | Noise | [10 empty] | 1 |  |  | Stuart Douglas | Carl Addington | Freddie Primus
|  | 41 |  |  |  |  | 19:08 |  | Go Power | [13 empty] | Gordon Stenseng | Brad Bryons | Dave Vanderwater
|  | 185 | 7100 |  |  |  | 19:55 |  | End of Fan (Maxwell self aborted firing loop causing a missed shot)
[23 empty] | Leigh Sauer | Bruce Marion | Marcello Di Campli
Fan6a | 189 | 189 | 7275 | 5150 |  | 6250 | 20:06 |  | Noise; Restarted Fan 6 | [10 empty] | 2 |  |  | Alex Plotnikov | Dave Richards | Leigh Sauer
|  | 221 |  |  |  |  | 20:15 |  | Go Power
|  | 413 | 7025 |  |  |  | 21:26 |  | End of Fan (Maxwell self aborted firing loop causing a missed shot, last good shot 380 @ 7050) | [13 empty] | Dave Vanderwater | Jim Minto | Gary Boche
[23 empty] | Carl Addington | Stuart Douglas | Gordon Stenseng
Fan6b | 415 | 415 | 7075 | 5150 |  | 6250 | 21:33 |  | Noise | [10 empty] | 3 |  |  | Pat Cummins | Gordon Stenseng | Alex Plotnikov
|  | 447 |  |  |  |  | 21:43 |  | Go Power | [13 empty] | Rick Strange |  | Pat Cummins
|  | 472 | 7075 |  |  |  | 21:55 |  | End of Fan (Vibro warning, Z-trac stopped sweeping) | [13 empty] | Larry Paterson |  | Camillo Zamponi
[23 empty] | Luke Wilkens |  | Tony Lagman
Fan6c | 473 | 473 | 7075 | 5150 |  | 6250 | 22:02 |  | Noise | [10 empty] | 4 |  |  | James Minto |  | Stuart Douglas
|  | 505 |  |  |  |  | 22:46 |  | Go Power | [15 empty] | Rick Strange
|  | 1080 | 6200 |  |  |  | 2:11 |  | End of Fan (Maxwell error "failed to connect to data server" last good shot 1016 @ 6300) | [15 empty] | Larry Paterson
Luke Wilkens
Fan6e | 1083 | 1083 | 6325 | 5150 |  | 6250 | 2:24 |  | Noise; Fan6d voided | [10 empty] | 5 |  |  |  |  | Andre Salesse
|  | 1115 |  |  |  |  | 2:33 |  | Go Power | [15 empty] | Conor Minto
|  | 1329 | 6000 |  |  |  | 3:50 |  | End of Fan (Maxwell error "failed to connect to data server" last good shot 1306 @ 6050) | [15 empty] | James Minto
Restart Maxwell and MCMP
Fan6f | 1331 | 1331 | 6075 | 5150 |  | 6250 | 4:12 |  | Noise | [10 empty] | 6
|  | 1379 |  |  |  |  | 4:23 |  | Go Power
|  | 2130 | 4900 |  |  |  | 8:32 |  | End of Fan End of Aqu. POH
Receiver well: |  |  | VSI(12) |  | 0 |  | Source S/N: |  |  | 30/31/03/06 | [5 empty] | Source Unit No.: |  | 3129
TARS Post Amp S/N well 1 / 2: |  |  | 0 |  | 0 |  | Source Type: |  |  | Z-Trak |  |  | Logging Speed: |  |  | Rec.Unit well 1/2: |  | 3019 |  | 0
TARS Comp.No.well 1 / 2: |  |  | 0 |  | 0 |  | Volts Pk-Pk: |  |  | 7.4 | Amps Pk-Pk: |  |  |  | 4 | Acquisition Op.: |  | G Baldovin / J Miller
Receiver Gain well: |  |  | 0 |  | 0 |  | Drive Level: |  |  | 386 | [5 empty] | QC Op.: |  | Brad / Carl |  |  |  |  | In
Analog Filter well 1 / 2: |  |  | 0 |  | 0 |  | SGF File Name: |  |  | 3129 | [5 empty] | Winch Op.: |  | J Chavez / D Vandawater |  |  |  |  | Out
Rev.5 2013
DEEPLOOK -CS

## Equip Failure Rpt-Step
Equipment Failure Report |  |  |  |  | Scroll for Fail/HSE/ NCR report | 2 | Equipment Failure Report |  |  |  | Scroll for Fail/HSE/ NCR report
Client: | URS |  |  | Date: | 2013-07-13 | Equip Failure Rpt-Step1 | Client: |  |  | Date:
Job No.: | 784 |  | Lost Time (hrs): |  | 0 |  | Job No.: |  | Lost Time (hrs):
Item Description: | Sorenson 2108 NB | [5 empty] | Item Description:
Part No.: |  |  |  | Serial No.: | 15 |  | Part No.: |  |  | Serial No.:
Description of Problem:- |  | OVP S/D light illuminated |  |  |  |  | Description of Problem:-
Equip Failure Rpt
HSE Report
Equip.Ser.Fail.
Equip Failure Rpt
HSE Report
Equip.Ser.Fail.
Trouble Shooting/Fault Finding Performed:- | [6 empty] | Trouble Shooting/Fault Finding Performed:-
Tried to reproduce the problem again using the test box (during the HFM part of the project). No success.
Will test the Sorenesen in the base during post job op-check.
Relevant Conditions (temp, depth, system config. etc):- | [6 empty] | Relevant Conditions (temp, depth, system config. etc):-
Reported By:- |  |  |  | Date: |  |  | Reported By:- |  |  | Date:
*** Make sure you submit an SQ RIR together with this Report and assign the appropriate Action Items ***
Rev.5 2013
[7 empty] | HSE Report |  |  |  | Scroll for Fail/HSE/ NCR report
[7 empty] | Client: |  |  | Date:
[7 empty] | Job No.: |  | Lost Time (hrs):
[7 empty] | Incident Type: | (ie; Near Miss / 1st Aid / Environmental / Other)
If 'Other' - Explain:
Description of Incident:-
Action Taken:-
Reported By:-
[7 empty] | Equipment Service Failure rpt |  |  |  | Scroll for Fail/HSE/ NCR report
[7 empty] | Client: |  |  | Date:
[7 empty] | Job No.: |  | Lost Time (hrs):
[7 empty] | Person Assigned to Deal With NCR:- |  | NCR Number:
Description of Non-conforming Situation:-
Choose ONE of the following;
Selection One:
Action Taken to eliminate the detected NCR:-
Selection Two
Authorize its use, release or acceptance under consession by a relavant authority and where applicable
by the customer:-
Selection Three:
Take action to preclude its original intended use or application:-
If re-worked was re-inspection done? (Yes/No):
[7 empty] | Final approval of Disposition By:- |  |  | Date:
DEEPLOOK -CS

## Equip Failure Rpt-Step (2)
Equipment Failure Report |  |  |  |  | Scroll for Fail/HSE/ NCR report | 2 | Equipment Failure Report |  |  |  | Scroll for Fail/HSE/ NCR report
Client: | URS |  |  | Date: | 2013-07-13 | Equip Failure Rpt-Step1 | Client: |  |  | Date:
Job No.: | 784 |  | Lost Time (hrs): |  | 0 |  | Job No.: |  | Lost Time (hrs):
Item Description: | Motorola radio | [5 empty] | Item Description:
Part No.: | AAM25KKD9AA2AN |  |  | Serial No.: | 103TNQ7228 |  | Part No.: |  |  | Serial No.:
Description of Problem:- |  | Motorola radio on source side having delays in firing |  |  |  |  | Description of Problem:-
Equip Failure Rpt
HSE Report
Equip.Ser.Fail.
Equip Failure Rpt
HSE Report
Equip.Ser.Fail.
Trouble Shooting/Fault Finding Performed:- | [6 empty] | Trouble Shooting/Fault Finding Performed:-
After a few trouble shooting it looks like the problem might be the VIBPRO unit. Taking out the VIBPRO
cards and re-seatting them seemd to work. No other source problem could be identified.
Relevant Conditions (temp, depth, system config. etc):- | [6 empty] | Relevant Conditions (temp, depth, system config. etc):-
Reported By:- |  |  |  | Date: |  |  | Reported By:- |  |  | Date:
*** Make sure you submit an SQ RIR together with this Report and assign the appropriate Action Items ***
Rev.5 2013
[7 empty] | HSE Report |  |  |  | Scroll for Fail/HSE/ NCR report
[7 empty] | Client: |  |  | Date:
[7 empty] | Job No.: |  | Lost Time (hrs):
[7 empty] | Incident Type: | (ie; Near Miss / 1st Aid / Environmental / Other)
If 'Other' - Explain:
Description of Incident:-
Action Taken:-
Reported By:-
[7 empty] | Equipment Service Failure rpt |  |  |  | Scroll for Fail/HSE/ NCR report
[7 empty] | Client: |  |  | Date:
[7 empty] | Job No.: |  | Lost Time (hrs):
[7 empty] | Person Assigned to Deal With NCR:- |  | NCR Number:
Description of Non-conforming Situation:-
Choose ONE of the following;
Selection One:
Action Taken to eliminate the detected NCR:-
Selection Two
Authorize its use, release or acceptance under consession by a relavant authority and where applicable
by the customer:-
Selection Three:
Take action to preclude its original intended use or application:-
If re-worked was re-inspection done? (Yes/No):
[7 empty] | Final approval of Disposition By:- |  |  | Date:
DEEPLOOK -CS

## Equip Failure Rpt-Step (3)
Equipment Failure Report |  |  |  | Scroll for Fail/HSE/ NCR report | 2 | Equipment Failure Report |  |  |  | Scroll for Fail/HSE/ NCR report
Client: | URS |  | Date: |  | Equip Failure Rpt-Step1 | Client: |  |  | Date:
Job No.: |  | Lost Time (hrs): |  |  |  | Job No.: |  | Lost Time (hrs):
Item Description: | [5 empty] | Item Description:
Part No.: |  |  | Serial No.: |  |  | Part No.: |  |  | Serial No.:
Description of Problem:- | [5 empty] | Description of Problem:-
Equip Failure Rpt
HSE Report
Equip.Ser.Fail.
Equip Failure Rpt
HSE Report
Equip.Ser.Fail.
Trouble Shooting/Fault Finding Performed:- | [5 empty] | Trouble Shooting/Fault Finding Performed:-
Relevant Conditions (temp, depth, system config. etc):- | [5 empty] | Relevant Conditions (temp, depth, system config. etc):-
Reported By:- |  |  | Date: |  |  | Reported By:- |  |  | Date:
*** Make sure you submit an SQ RIR together with this Report and assign the appropriate Action Items ***
Rev.5 2013
[6 empty] | HSE Report |  |  |  | Scroll for Fail/HSE/ NCR report
[6 empty] | Client: |  |  | Date:
[6 empty] | Job No.: |  | Lost Time (hrs):
[6 empty] | Incident Type: | (ie; Near Miss / 1st Aid / Environmental / Other)
If 'Other' - Explain:
Description of Incident:-
Action Taken:-
Reported By:-
[6 empty] | Equipment Service Failure rpt |  |  |  | Scroll for Fail/HSE/ NCR report
[6 empty] | Client: |  |  | Date:
[6 empty] | Job No.: |  | Lost Time (hrs):
[6 empty] | Person Assigned to Deal With NCR:- |  | NCR Number:
Description of Non-conforming Situation:-
Choose ONE of the following;
Selection One:
Action Taken to eliminate the detected NCR:-
Selection Two
Authorize its use, release or acceptance under consession by a relavant authority and where applicable
by the customer:-
Selection Three:
Take action to preclude its original intended use or application:-
If re-worked was re-inspection done? (Yes/No):
[6 empty] | Final approval of Disposition By:- |  |  | Date:
DEEPLOOK -CS

## Post Job Info-Step
Post Job Downhole Equipment
Information for Lab | [6 empty] | Post Job Info-Step1
Client: | URS
Area: | COP 324
Project #: | 784
Start Date: | 7-11,12,13 and 7-19,20,21
| Source Primary | Source Backup | TARS Primary | TARS Remote | TARS Backup | Geophone
Serial # | 3,6,31,30 | 32,33
Approx. time in hole | 6 days total | 0
Max temp |  | 0
Max Depth | 7300 ft | 0
Fluid in hole | water | 0
Gas
H2S
Shipping Method | shipping box/ trailer | same
Shipping Distance | shreveport La. to clearfield Pa. | same
Any Problems
Description of unusual well conditions: |  |  | fluid level 2250 ft
Description of Tool Problems: |  |  | na
Unusual Operating procedures: |  |  | na
Rev.5 2013
DEEPLOOK -CS