2/22 report:

- Jerry and Anthony started to clear a platform for the well area, as well as clearing a small area for the trailer

- No major struggles or other complications, other than dealing with morning frost and damp topsoil

- Both J & A were working safely and taking regular sandwich and water breaks

2/23 report:

- Continual clearing of a well platform. Jerry mentioned that they will be pushing dirt for the remainder of this week, and ready for the next phase of laying boards down by Monday or Tuesday, if weather holds.

- Jerry took off around noon for a medical appointment, and was relieved by Corey

- No major issues or safety violations.

2/24 report:

- Getting down to the "good" dirt according to Jerry (the red stuff), and making swift progress. Dirt pile is growing over 6ft along the perimeter.

- Hoping the rain today through this weekend doesn't halt any progress. Rain will dictate how much work will need to be done this weekend, if any.

- Wellsite manager supposed to be stopping by this morning.

- And everyone is being safe and cozy

2/25 report:

- Wellsite manager came by yesterday and proposed to extend the drilling area by about 50 ft to one side so there's enough room for pumps and ramp onto rig, which apparently makes things too clustered if theyre in the 4000 ft2 area

- Jerry estimates that the building of the drill site should be done by middle of next week

- Making great headway with clearing the platform. Had all 3 guys out there yesterday pushing dirt.

- Rain held off yesterday but its calling for more over the next few days, so we'll see if that will stall any progress.

3/3

Weather is great here now after lots of rain early in the week. It was still pretty wet yesterday and Jerry was only able to skim the top layer off to try and dry it out and get it ready for today. He's moving dirt today and starting the silt fence. He thinks he'll be done Friday or early Saturday.

3/4

Today the silt fence got put up and they continued moving dirt. They have some more dirt to move tomorrow before putting in the cellar in. Should just be smoothing it over and dressing it up on Saturday.

3/6

There was rain Monday (3/1/2021) and Tuesday (3/2/2021) that delayed site development at the Castle well location until Wednesday afternoon. Thursday (3/4/2021) Singley construction continued to cut dirt and move it across the south end of the site, and they put it up the silt fence around the site. Friday (3/5/2021) Singley put in the well cellar and continued to move dirt around the site to ensure the rig will sit on flat ground. Representatives from Deepwell (boarding company) and WT drilling stopped by to see the site. Saturday (3/6/2021) Anthony, one of Singley's operators, finished cleaning up the site and smoothing everything over around noon. The castle site is ready to be boarded the following week.