BEG CO2 SEQUESTERATION PROJECT
LIBERTY FIELD TEST WELL DRILLING AND COMPLETION PLAN

Conductor Hole

- Prepare surface location.

- Pick up hammer and drive 14” (.375” wall) conductor to +/-80 feet.  Install temporary 13-5/8” 3M X 13-3/8” weld-on flange onto conductor pipe.

Surface Hole

- Mobilize and rig-up drilling rig.

- Drill mousehole and rathole.

- Install 13-5/8” 3M drilling spool and 13-5/8” 3M annular preventer on conductor.

- Nipple up bell nipple, flow line, and diverter line.  Pressure-test annular BOP and related equipment to 200 psig.

- Drill a 12-1/4 inch surface hole to +/- 3,650 feet.  Short trip as necessary to reduce drag.

- Rig up wireline equipment and run openhole electric logs.

- Make conditioning trip for running casing if necessary.

- Run 9-5/8” 43.5 lb/ft J-55 STC surface casing with cementing stage collar at approximately 2,000 feet.

- Cement surface casing from 3,650 feet to surface in two stages.  Wait on cement a minimum of 8 hours.

- Cut surface casing and install 11-inch 3,000 psi slip-on wellhead.

Production Hole

- Rig up rig well control equipment & drill out stage collar, float collar, and shoe cement to within 15 ft of casing shoe with 8-1/2” bit.

- Make casing scraper run to top of cement.

- Run casing inspection logs (temperature survey, cement bond log).

- Pick up 8-1/2” steerable drilling assembly and lower to top of cement.  Pressure-test surface casing to 1,500 psig.  Drill out casing shoe and conduct leakoff test.

- Drill 8-1/2” hole, steering as necessary for directional control, to approximately 4,900 feet (core point).

- Retrieve drilling assembly and pick up coring assembly.  Cut a 30-foot conventional core and retrieve coring assembly.

- Pick up drilling assembly and ream the cored section of hole to 8-1/2” diameter.

- Continue drilling to the next core point, estimated at 5,200 feet.  Retrieve drilling assembly and pick up coring assembly.

- Cut a 30-foot conventional core and retrieve coring assembly.

- Pick up drilling assembly and ream the cored section of hole to 8-1/2” diameter.

- Continue drilling the well to proposed total depth of 5,500 feet.

- Insert a drop gyro into the workstring, and retrieve drilling assembly while taking a gyro multi-shot survey over the course of the wellbore.

- Run desired open hole logging suite and obtain sidewall cores as needed to obtain appropriate reservoir data.  Make conditioning trip while logging if needed to ensure hole stability.

- Make a conditioning trip and retrieve the workstring, laying it down.

- Run 7” 29.7 lb/ft N-80 LT&C protection casing with cementing stage collar at approximately 3,500 feet.

- Cement protection casing from 5,500 feet to surface in two stages.

- Make a rough cut on casing, nipple down well control equipment, and rig down drilling rig.

- Install 7-1/16” wellhead.  Install blind flange on wellhead.

Completion Procedure

- Mobilize a workover rig to wellsite and rig up.  Nipple up 7-1/16” 3M well control equipment.

- Pick up a 6-1/8” bit, drill collars (4-3/4-inch), and 2-7/8” workstring and trip into the hole to the stage collar.  Drill out dart and trip in the hole to bottom.  Drill out cement to within 15 feet of the float shoe.  Circulate bottoms up and pull out of the hole.

- Pick up bit and casing scraper and trip in the hole to bottom.  Circulate bottoms up and pull out of the hole.

- Nipple up wireline lubricator to the top of the BOP stack.  Pressure test to 2,000 psig.  Run temperature survey from surface to top of cement at +/- 5,785 feet.  Run cement bond and casing inspection logs.  Run CBL under elevated pressures if necessary.

- Pick up 6-1/8” bit and casing scraper and trip to bottom.  Pressure-test the casing to 1,500 psig for 30 minutes.

- Displace drilling fluid from wellbore with completion brine.  Pickle workstring with acid or other cleaning agent.

- After clean fluids are present throughout wellbore, pull end of workstring up to desired depth.  The selected depth will be calculated to achieve an underbalance of 500 to 1,000 psi using fresh water to displace completion brine at that depth.

- Rig up wireline equipment and install hollow carrier perforating guns (loaded at approximately 12 shots/foot) on wireline.  Lower the guns to bottom and position on depth using GR/CCL to correlate with well logs.  Actuate guns and perforate the 7-inch protection casing in the Injection Interval.  Retrieve perforating gun and rig down wireline equipment.

- Pick up 6-1/8” bit on 2-7/8” workstring and trip in the hole to the bottom of the well and circulate out sand/perforation debris.

- Pull out of the hole laying down workstring.

- Rig up tubing running and connection test equipment.  Pick up 2-7/8” X 7” injection packer.  Make up pressure sensor tools and seating nipple(s) on tail pipe and attach to packer.

- Run 2-7/8” injection tubing string with seismic array included to desired packer-setting depth.  Externally connection-test each joint of tubing to 2,500 psig while making up tubing string.

- Displace annular fluid with filtered packer fluid.

- Space out tubing and land hanger in wellhead.

- Rig up slickline unit and set plug in nipple below packer.  Set injection packer by pressuring up on tubing.  Conduct preliminary annulus pressure test to 1,050 psig to ensure packer is set properly.

- Retrieve plug from tubing and rig down slickline unit.

- Nipple down BOPs and install and test surface wellhead.

- Clean tanks, rig down workover rig, and move off location.